## Product Backlog
No | Name | Role | Features | Description | Added in sprint
1 | Home page | User | Default page | Default page of website includes main information of the website
2 | Authentication | User | Login / logout | Users can access their account and use support features.
3 |  |  | Register | Register to become a website member
4 |  |  | Get forgotten password | Users are able to reset password via registered email if they forget their password.
5 |  | Admin | Website controller | Access to website controler (Dashboard page)
6 | Website dashboard | Admin | Manage website member | view, delete, create, update website's member
7 |  |  | Manage member type | change member type's support features
8 | Personalisation | Authenticated user | User's profile | They are able to manage their own profile information.
9 | Template/theme page | Authenticated user | View template/theme | They can view/choose available template/them
10 |  |  | Search template/theme | Search for matching template/theme by main color, display type
11 |  |  | Handle created sites | Allow view site's status, created site history, create new or remove created template.
12 | Site builder | Authenticated user | Build page content | Drag & drop site element
13 |  |  | View under two different devices | User be able to design website under different devices's view (mobile or desktop)
14 |  |  | Format site | Choose layout, font type, backgroud
15 |  |  | Design pages | insert, delete website pages
16 | Product Management | Site owner | manage product's information | update, insert, delete product's details information
17 |  |  | control and view statictis | control and view statictis of the website.
18 | Website mapping domain | Authenticated user | map exist domain | access new template/theme with current domain
19 |  |  | generate a sub-domain | access created product catalogue site via generated subdomain.

## Sprint 1
Sprint 1 |  |  | Start | 13/01/2015
|  |  | End | 20/01/2015
No | Task | Description | Person in charge |  | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Design homepage theme | Using bootstrap, Jquery to create a responsive page, flat design | DuyPK |  | In Process | 20 | 0 | 0
2 | Design register/login/logout page | Login/register are show as a pop-up, support identity identifier (facebook, google) | DuyPK |  | Not Started | 2 | 0 | 0
3 | Design dashboard page |  | TuanLD |  | In Process | 10 | 0 | 0
4 | Design site buider page |  | TuanLD |  | Not Started | 10 | 0 | 0
5 | Design ERD | Using Microsoft Visio/StarUML (UML 2.0) | ThinhLT |  | In Process | 10 | 0 | 0 | 2
6 | Design Usecase |  | ThangPV |  | In Process | 20 | 0 | 0 | 4
7 | Design Systems Architect |  | TuanLD |  | Not Started | 2 | 0 | 0
8 | Design Physical Database |  | ThinhLT |  | Not Started | 2 | 0 | 0
9 | Report 2:
| 1- Project definition |  | TuanLD |  | Finished | 4 | 3 | 1
| 2- Project oganization |  | DuyPK |  | Finished | 4 | 2 | 2
| 3- Project management plan |  | ThinhLT |  | Finished | 4 | 2 | 2
| 4- Coding convention |  | ThinhLT |  | Finished | 1 | 0 | 1
| Report review |  | ThangPV |  | Finished | 2 | 0 | 2

## Refrence
Not Started
In Process
Approved
Finished