## Product Backlog
No | Name | Role | Features | Description | Added in sprint
1 | Home page | User | Default page | Default page of website includes main information of the website
2 | Authentication | User | Login / logout | Users can access their account and use support features.
3 |  |  | Register | Register to become a website member
4 |  |  | Get forgotten password | Users are able to reset password via registered email if they forget their password.
5 |  | Admin | Website controller | Access to website controler (Dashboard page)
6 | Website dashboard | Admin | Manage website member | view, delete, create, update website's member
7 |  |  | Manage member type | change member type's support features
8 | Personalisation | Authenticated user | User's profile | They are able to manage their own profile information.
9 | Template/theme page | Authenticated user | View template/theme | They can view/choose available template/them
10 |  |  | Search template/theme | Search for matching template/theme by main color, display type
11 |  |  | Handle created sites | Allow view site's status, created site history, create new or remove created template.
12 | Site builder | Authenticated user | Build page content | Drag & drop site element
13 |  |  | View under two different devices | User be able to design website under different devices's view (mobile or desktop)
14 |  |  | Format site | Choose layout, font type, backgroud
15 |  |  | Design pages | insert, delete website pages
16 | Product Management | Site owner | manage product's information | update, insert, delete product's details information
17 |  |  | control and view statictis | control and view statictis of the website.
18 | Website mapping domain | Authenticated user | map exist domain | access new template/theme with current domain
19 |  |  | generate a sub-domain | access created product catalogue site via generated subdomain.

## Sprint 1
Sprint 1 |  |  | Start | 13/01/2015
|  |  | End | 20/01/2015
No | Task | Description | Person in charge |  | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Design homepage theme | Using bootstrap, Jquery to create a responsive page, flat design | DuyPK |  | Finished | 10 | 0 | 0 | 0 | 0 | 0 | 5 | 0
2 | Design register/login/logout page | Login/register are show as a pop-up, support identity identifier (facebook, google) | DuyPK |  | Finished | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 0
3 | Design user dashboard page |  | DuyPK |  | Finished | 10 | 0 | 0 | 0 | 0 | 0
4 | Design Admin dashboard page |  | TuanLT |  | Finished | 10 | 0 | 2 | 4 | 0 | 0 | 0 | 0
5 | Design site buider page |  | TuanLT |  | Finished | 10 | 0 | 0 | 1 | 3 | 2 | 2 | 0
6 | Design ERD | Using Microsoft Visio/StarUML (UML 2.0) | ThinhLT |  | Finished | 10 | 0 | 0 | 2 | 2 | 2 | 2 | 2
7 | Design Usecase |  | ThangPV |  | Finished | 20 | 0 | 0 | 2 | 2 | 3 | 5 | 5
8 | Design Systems Architect |  | TuanLT |  | In Process | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2
9 | Design Physical Database |  | ThinhLT |  | Finished | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
10 | Report 2:
| 1- Project definition |  | TuanLT |  | Finished | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0
| 2- Project oganization |  | DuyPK |  | Finished | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| 3- Project management plan |  | ThinhLT |  | Finished | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| 4- Coding convention |  | ThinhLT |  | Finished | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| Report review |  | ThangPV |  | Finished | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0

## Sprint 2
Sprint 2 |  |  | Start | 20/01/2015
|  |  | End | 27/01/2015
No | Task | Description | Person in charge |  | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Design Systems Architect | Not complete in sprint 1 | TuanLT |  | Finished | 2 | 2
3 | Design Home page |  | ThangPV |  | Finished | 2 | 0 | 2 | 0
4 | Design authentication |  |  |  | Finished | 2 | 0 | 0 | 2
5 | 1. Design Admin Dashboard |  | DuyPK |  | Not Started | 2
6 | 1.1 Design User management |  |  |  | Not Started | 2
7 | 1.2 Design Account type management |  |  |  | Not Started | 2
8 | 1.3 Design Template management |  |  |  | Not Started | 2
9 | 2. Design User dashboard |  | ThinhLT |  | Not Started | 2
10 | 2.1 Design Profile management |  |  |  | Not Started | 2
11 | 2.2 Design account type, check out |  |  |  | Not Started | 2
12 | 2.3 Design Site management(Edit, remove, duplicate) |  |  |  | Not Started | 2
13 | 2.4 Design statistic management |  |  |  | Not Started | 2
14 | 2.5 Design site builder |  | TuanLT |  | In Process | 2
15 | 2.5.1 Design search, view template |  |  |  | Not Started | 2
16 | 2.5.2 Design site layout builder |  |  |  | Not Started | 2
17 | 2.5.3 Design site elements builder |  |  |  | Not Started | 2
18 | 2.5.4 Design site page builder |  |  |  | Finished | 2 |  |  | 1.5
19 | 2.5.5 Design product management(CRUD) |  |  |  | In Process | 2
20 | 2.5.6 Design map domain |  |  |  | Not Started | 2
21 | Review and merge |  | ThangPV |  | In Process | 5 |  |  | 2 | 2
1 | Report 3: SRS
| 1. User Requirement Specification |  | ThinhLT |  | Not Started | 4
2. System Requirement Specification
2.1 External Interface Requirement
| 2.2 System Overview Use Case | Continue sprint 1, design usecase | ThangPV |  | In Process | 10
| 3. Software System Attribute |  | TuanLT |  | Not Started | 4
| 4. Conceptual Diagram |  |  |  | Not Started
| Review |  | ThangPV |  | Not Started | 2

## Temporary Performance Rate
SPRINT 2
Date | Team member | Task | Description | Performance Point
Day 4 23/01 | ThinhLT | ERD | Not meet the deadline: Lack of some enities, confuse about entity relation | 6
|  | 2.1 Design Profile management | Not working on it | 0
| TuanLT | Design site page builder | In time | 9
| DuyPK | Design | Not working on it | 0
Day 5 24/01 | ThinhLT | 2.1 Design Profile management | Not meet the deadline. Delay 1 former task Not fill in the backlog | 2
| TuanLT | Design | In time Need more focus to complete assigned task | 9
| DuyPK | Design | Not working on it | 0
Day 6 25/01 | ThinhLT | Design
| TuanLT | Design
| DuyPK | Design
Day 7 26/01 | ThinhLT | Design
| TuanLT | Design
| DuyPK | Design

## Refrence
Not Started
In Process
Wait for approve
Finished