## Product Backlog
No | Name | Role | Features | Description | Added in sprint
1 | Home page | User | Default page | Default page of website includes main information of the website
2 | Authentication | User | Login / logout | Users can access their account and use support features.
3 |  |  | Register | Register to become a website member
4 |  |  | Get forgotten password | Users are able to reset password via registered email if they forget their password.
5 |  | Admin | Website controller | Access to website controler (Dashboard page)
6 | Website dashboard | Admin | Manage website member | view, delete, create, update website's member
7 |  |  | Manage member type | change member type's support features
8 | Personalisation | Authenticated user | User's profile | They are able to manage their own profile information.
9 | Template/theme page | Authenticated user | View template/theme | They can view/choose available template/them
10 |  |  | Search template/theme | Search for matching template/theme by main color, display type
11 |  |  | Handle created sites | Allow view site's status, created site history, create new or remove created template.
12 | Site builder | Authenticated user | Build page content | Drag & drop site element
13 |  |  | View under two different devices | User be able to design website under different devices's view (mobile or desktop)
14 |  |  | Format site | Choose layout, font type, backgroud
15 |  |  | Design pages | insert, delete website pages
16 | Product Management | Site owner | manage product's information | update, insert, delete product's details information
17 |  |  | control and view statictis | control and view statictis of the website.
18 | Website mapping domain | Authenticated user | map exist domain | access new template/theme with current domain
19 |  |  | generate a sub-domain | access created product catalogue site via generated subdomain.

## Sprint 1
Sprint 1 |  |  | Start | 13/01/2015
|  |  | End | 20/01/2015
No | Task | Description | Person in charge |  | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Design homepage theme | Using bootstrap, Jquery to create a responsive page, flat design | DuyPK |  | Finished | 10 | 0 | 0 | 0 | 0 | 0 | 5 | 0
2 | Design register/login/logout page | Login/register are show as a pop-up, support identity identifier (facebook, google) | DuyPK |  | Finished | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 0
3 | Design user dashboard page |  | DuyPK |  | Finished | 10 | 0 | 0 | 0 | 0 | 0
4 | Design Admin dashboard page |  | TuanLT |  | Finished | 10 | 0 | 2 | 4 | 0 | 0 | 0 | 0
5 | Design site buider page |  | TuanLT |  | Finished | 10 | 0 | 0 | 1 | 3 | 2 | 2 | 0
6 | Design ERD | Using Microsoft Visio/StarUML (UML 2.0) | ThinhLT |  | Finished | 10 | 0 | 0 | 2 | 2 | 2 | 2 | 2
7 | Design Usecase |  | ThangPV |  | Finished | 20 | 0 | 0 | 2 | 2 | 3 | 5 | 5
8 | Design Systems Architect |  | TuanLT |  | In Process | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2
9 | Design Physical Database |  | ThinhLT |  | Finished | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
10 | Report 2:
| 1- Project definition |  | TuanLT |  | Finished | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0
| 2- Project oganization |  | DuyPK |  | Finished | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| 3- Project management plan |  | ThinhLT |  | Finished | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| 4- Coding convention |  | ThinhLT |  | Finished | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| Report review |  | ThangPV |  | Finished | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0

## Sprint 2
Sprint 2 |  |  | Start | 20/01/2015
|  |  | End | 27/01/2015
No | Task | Description | Person in charge |  | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Design Systems Architect | Not complete in sprint 1 | TuanLT |  | Finished | 2 | 2 | 0 | 0 | 0 | 0 | 0
3 | Design Home page |  | ThangPV |  | Finished | 2 | 0 | 2 | 0 | 0 | 0 | 0
4 | Design authentication |  |  |  | Finished | 2 | 0 | 0 | 2 | 0 | 0 | 0
5 | 1. Design Admin Dashboard |  | DuyPK |  | Finished | 2
6 | 1.1 Design User management |  | DuyPK |  | In Process | 2
7 | 1.2 Design Account type management |  | DuyPK |  | In Process | 2
8 | 1.3 Design Template management |  | DuyPK |  | In Process | 2
9 | 2. Design User dashboard
10 | 2.1 Design Profile management |  | ThinhLT |  | In Process | 2 | 0 | 0 | 0 | 0 | 2 | 0
11 | 2.2 Design account type, check out |  | ThinhLT |  | In Process | 2 | 0 | 0 | 0 | 0 | 1 | 1
12 | 2.3 Design Site management(Edit, remove, duplicate) |  | ThinhLT |  | Finished | 2 | 0 | 0 | 0 | 0 | 0 | 2
13 | 2.4 Design statistic management |  | ThinhLT |  | In Process | 2 | 0 | 0 | 0 | 0 | 0 | 1
14 | 2.5 Design site builder
15 | 2.5.1 Design search, view template |  | TuanLT |  | In Process | 2 | 0 | 0 | 1 | 0 | 0 | 1
16 | 2.5.2 Design site layout builder |  | TuanLT |  | Not Started | 2
17 | 2.5.3 Design site elements builder |  | TuanLT |  | Finished | 2 | 0 | 0 | 2 | 2 | 1 | 0
18 | 2.5.4 Design site page builder |  | TuanLT |  | In Process | 2 | 0 | 0 | 0 | 0 | 0 | 1
19 | 2.5.5 Design product management(CRUD) |  | TuanLT |  | Finished | 2 | 0 | 0 | 0 | 2 | 2 | 0
20 | 2.5.6 Design map domain |  | TuanLT |  | Finished | 2 | 0 | 0 | 0 | 0 | 1 | 2
| Member | Performance Point
| TuanLT | 7
| ThinhLT | 5
| DuyPK | 5
| ThangPV | 4

## Sprint 3
Sprint 3 |  |  | Start | 27/01/2015
|  |  | End | 2015-03-02
No | Task | Description | Person in charge |  | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Design User management | Continue form sprint 2 | DuyPK |  | In Process | 1
2 | Design Account type management |  | DuyPK |  | In Process | 1
3 | Design Template management |  | DuyPK |  | In Process | 1
4 | Design Profile management |  | ThinhLT |  | Finished | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0
5 | Design account type, check out |  | ThinhLT |  | Finished | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0
6 | Design statistic management |  | ThinhLT |  | Finished | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
7 | Design search, view template |  | TuanLT |  | Finished | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
8 | Design site page builder |  | TuanLT |  | Finished | 5 | 0 | 2 | 2 | 2 | 3 | 0 | 0
9 | Design site layout builder |  | TuanLT |  | Finished | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0
10 | Class diagram |  | TuanLT |  | Finished | 8 | 0 | 2 | 3 | 0 | 0 | 0 | 0
11 | Design some template for builder | Design 3 to 4 separate 'n simple template which include 2 file: index.html (define layout structure) and style.css. In index.html must be defined 5 basic components: title, navigation menu, header, main container and footer. While main container is the bank space allows drag n drop element inside. Every id/class have a simple definition name is a must. | DuyPK |  | In Process | 13
12 | Create project database | Using entity framwork, code first approach | ThangPV |  | Finished | 10 | 2 | 2 | 2 | 2 | 2 | 0 | 0
13 | Code Authentication, authorization |  | ThinhLT |  | In Process | 10 | 0 | 0 | 0 | 0 | 0 | 5 | 0
14 | Code send automatic email function | By using SMTP API of sendgrid.com, include create email template. | ThinhLT |  | Finished | 15 | 0 | 0 | 0 | 0 | 0 | 2 | 10
15 | Code validate function | implement some available validation in project: register, domain, edit form etc... | TuanLT |  | Finished | 12 | 0 | 0 | 0 | 2 | 2 | 2 | 0
16 | Code example Drag n Drop function |  | ThangPV |  | Finished | 12 | 0 | 0 | 3 | 3 | 3 | 3 | 0
17 | Task review |  | ThangPV |  | Finished | 6 | 0 | 0 | 0 | 2 | 0 | 0 | 4
18 | Report 3: SRS
| 1. User Requirement Specification |  | DuyPK |  | Not Started | 12
2. System Requirement Specification
2.1 External Interface Requirement
| Total task | Finished | Inprocess
| 18 | 12 | 6
|  | total task | finished | Percent
| TuanLT | 28 | 28 | 100%
| ThinhLT | 28 | 23 | 82.14%
| DuyPK | 28 | 0 | 0%
| ThangPV | 28 | 28 | 100%

## Sprint 4
Sprint 4 |  |  | Start | 2015-03-02
|  |  | End | 2015-10-02
No | Task | Description | Person in charge |  | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Design User management | Continue form sprint 2 | DuyPK |  | In Process | 1
2 | Design Account type management |  | DuyPK |  | In Process | 1
3 | Design Template management |  | DuyPK |  | In Process | 1
4 | Code JS module for editable element |  | ThinhLT |  | Wait for approve | 18 |  |  |  |  | 5 | 5 | 8
5 | Code JS module for 'drag drop' fuctions |  | ThangPV |  | In Process | 18
6 | Code JS module for changing layout / style |  | TuanLT |  | In Process | 18 |  |  | 2
7 | Code module for creating subdomain |  | DuyPK |  | Not Started | 18
8 | Business logic for user management |  | DuyPK |  | Not Started | 10
9 | Business logic for account type management |  | ThangPV |  | In Process | 10
10 | Business logic for register |  | ThinhLT |  | Wait for approve | 10 |  | 8 |  |  |  |  | 2
11 | Design category management page |  | TuanLT |  | In Process | 10 |  | 2 | 2
12 | Design some template for builder | Design 3 to 4 separate 'n simple template which include 2 file: index.html (define layout structure) and style.css. In index.html must be defined 5 basic components: title, navigation menu, header, main container and footer. While main container is the bank space allows drag n drop element inside. Every id/class have a simple definition name is a must. | DuyPK |  | In Process | 13
13 | Code Authentication, authorization |  | ThinhLT |  | Wait for approve | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0
14 | Report 3: SRS
| 1. User Requirement Specification |  | DuyPK |  | Not Started | 12
2. System Requirement Specification
2.1 External Interface Requirement
| Total task | Finished | Inprocess
|  | total task | finished | Percent
TuanLT
ThinhLT
DuyPK
ThangPV

## Task's comment
Task | Comment | Person in charge
Design Profile management | lack of showing the account type | ThinhLT
Design statistic management | need a little bit adjusting in right side bar | ThinhLT
Design statistic management | Misspelled word "Unlimit sites" | ThinhLT
Code validate function (Only login and adding new products) | Form error in "Add new product" page Validation message should better be shown below the text box. | TuanLT
Design search, view template | lack of search function template should be shown in the center | TuanLT
Design site layout builder Design site page builder | UI is a bit weird, "layout builder" should be link to another page | TuanLT

## Refrence
Not Started
In Process
Wait for approve
Finished